## Sheet1
S. No | Requirement Details | Priority | Impl. Level | Completion Date | Status | Comments
LOGIN
1 | Online authentication on every login. Use sms.sirentext.co.in check balance API for authentication. | High | High | 2016-06-16
2 | Save password option | Medium | Medium
Display password option
3 | Provide contact info on login failure. | Low | Low | 2016-06-17 |  | Added as part of error message
Provide 'how to register' info on login page - Required?
4 | Hide the keyboard on app startup. Display keyboard only when user clicks on EditText | Low | Low | 2016-06-06 |  | http://stackoverflow.com/questions/1555109/stop-edittext-from-gaining-focus-at-activity-startup
5
6
SUMMARY
1 | Summary Display: Company name (from preferences) | High | Low
2 | Summary Display: Company logo? | High | High
3 | Summary Display: Total number of contacts | High | Medium
4 | Summary Display: Number of contacts added last day | High | Medium
5 | Summary Display: Number of contacts added last month | High | Medium
6 | Display admin options (like survey list, settings etc) only after admin login | Medium | Medium | 2016-06-07 |  | http://stackoverflow.com/questions/30918026/change-navigationview-items-when-user-is-logged
| Summary Display: SMS balance | Medium | Medium
7
USER PROFILE ON NAVIGATION VIEW
1 | Display user name, image and other details on left pane. Use static offline data now. | High | Low | 2016-06-07
2 | Get the shop name from the value entered on preferences | High | Low
3 | Get the email id from the value entered on login | High | Low
4 | Get the image to be used for user profile from the local gallery and save it in app space. Give option in the settings somehow. | Medium | High
5
SURVEY LIST
1 | Option: Sort -> By Name
2 | Option: Sort -> By Shopping date
3 | Option: Sort -> By Date of birth (don’t consider year in this option)
4 | Option: Filter -> Last day shoppers
5 | Option: Filter -> Last month shoppers
6 | Option: Filter -> Birthday today
7 | Option: Filter -> Birthday this month
8 | Option: Filter -> Birthday next 30 days
9 | Option: Filter -> Birthday next 7 days
10 | Option: Filter -> Group - How to effectively display the UI in this case since there are many groups?
11 | Option: Find - Let the user find a contact by name
12 | Implement complex filters with combinations - like last month and a gender and this category purchase. Etc | Low | High |  |  | SQL query will be easy. But creating a UI for creating the query will be difficult.
13 | Send SMS to the selected group (multiple senders) | High | Medium | 2016-06-06 |  | Support from SurveyList is done
14 | User should be able to select the users to send SMS - either using filters or using checks. The list to support check mark to select users. | Medium | Medium
15 | Option: Export contacts - Generate a web compatible file of the required format (excel, CSV etc) and store it to SD card for importing the mobile contacts to web. | Low | High
Option: Import contacts - Accept a compatible file to update the contact list
| Optimize DB read to query for only those columns which are displayed in the list | Low | Low
| Issue: Pressing OK on a sorted list (otherthan default sorted), the details screen launches with wrong contact details | High | Low |  |  | Use the same cursor used by surveyList
SURVEY
1 | Store in DB: Gender (RadioButtons) | Low | Medium | 2016-06-15
2 | Store in DB: Date of Birth | Low | Medium | 2016-06-15
3 | Store in DB: Date of purchase (get time at the time of form submission) | Hgh | Medium | 2016-06-15
4 | Store in DB: User groups (It can be more than one, so think about having a different table)
5 | Store in DB: New user group while adding a new contact. This user group should be accessible from the next contact or in the survey list page
6 | Store in DB: Interested categories for the user
7 | Modify the date input to dialog for DOB and date of purchase | Medium | Medium | 2016-06-15
8 | Hide the keyboard on launch of screen
9 | Optionally bringup a feedback form - Phase 2
10 | Issue: Next from softkeyboard from mobile number. Select default radio button. Try to change radio option. App crashes
Issue: Storing the date of birth as absolute milliseconds now. This will not be suitable for DB filtering for DOB irrespective of year. Store only day and month.
Check optional and mandatory parameters before submit
Send Welcome SMS on adding new customer.
Get the provision to configure a welcome SMS
11
SURVEY DETAILS
1 | Display: Name | Low | Low | 2016-06-15
2 | Display: Phone number | Low | Low | 2016-06-15
3 | Display: Email ID | Low | Low | 2016-06-15
4 | Display: Contacts group | High | High
5 | Display: Gender | Low | Low | 2016-06-15
6 | Display: Place | Low | Low | 2016-06-15
7 | Display: Date of birth | Low | Low | 2016-06-15
8 | Display: Date of shopping | Low | Low | 2016-06-15
9 | Display: Index of current customer out of total number of customers (like 2 of 23) | Low | Low | 2016-06-15
10 | Highlight if there is any special occurances - like if birthday of the user is today or falls in this month etc. | Low | Medium |  |  | Identify what to display
11 | Allw a contact to be added to another group | Low | Medium
12
GENERAL
1 | Correct the UI layout to match to a theme | High | High
2 | Press back key twice to exit the app | Low | Low | 2016-06-06 |  | http://stackoverflow.com/questions/8430805/clicking-the-back-button-twice-to-exit-an-activity
3 | Reword the activity titles, options etc (Survey to Customer/Contacts etc) | High | Low
Bringup a splash screen with loading icon, company logo etc on startup (before showing login page)
4 | Check network connection on splash screen. Load login page only if there is network connection. Otherwise, display an error message. | High | Medium
Read and set default preferences while displaying splash screen
5
SEND SMS
1 | Store the sent SMS details on DB. Create a provision to view them later. A list layout will do. | Low | Medium
2 | Pass the target mobile numbers from the previous activity and display it. User will be able to edit the numbers but will not be able to add new numbers. User will be able to compose the message and send it. Will be applicable from SueveryList and SurveyDetails. | High | Low | 2016-06-06
3 | Implement and test the actual SMS sending functionality - for single number. Get the number from EditText and send the SMS | High | Medium | 2016-06-07 |  | http://stackoverflow.com/questions/14065910/sending-sms-programmatically-to-multiple-people-getting-generic-error
4 | Implement and test the actual SMS sending functionality - for multiple numbers. This needs the parsing of the numbers from EditText also to cater for possible editings. | High | Medium | 2016-06-07
5 | Integrate a sample bulk SMS gateway functionality to the app. Give the option in settings. | High | Medium | 2016-06-13
6 | Send SMS Optimization - In a different thread (AsyncTask) | Medium | Medium | 2016-06-13
7 | Display error message when user cancels the 'Please wait' dialog during online sms async task | Medium | Medium
8 | Check for network connection before sending online SMS and display warning if not connected according to user preferences (Wifi, mobile data etc) | Medium | Medium
9 | Modifications are required for user cancellation during SMS sending, displaying progress, handling no/poor internet connection, network disconnection during SMS sending | Medium | Medium
10 | Allow SIM SMS only when a SIM is inserted | Medium | Medium
11 | Integrate the sirentext APIs to send the SMS | High | Medium | 2016-06-16
12 | Display the SMS balance in the SendSMS screen | Medium | Medium
Send to group option.
| Make sure the maximum number of mobile numbers in a single POST method is 100 for sirentext | High | Medium | 2016-06-16
SMS Templates - Add templates
SETTINGS
1 | Configure: Shop name | Low | Low
2 | Configure: Image in gallery to be used as the shop picture. Give option for trimming/resizing | Low | High
3 | Configure: Network preference - wifi, mobile data or both???? | Low | High
4 | Configure: Contacts categories - Add/delete? | Low | High
5 | Configure: Shopping categories - Add/delete? | Low | High
6 | Configure: Allow/disallow contacts to be added to multiple contact groups | Low | High
7 | Configure: Change admin password. Bring a dialog. Enter current password, new password 2 times. Persist | Low | Medium
| Configure: Enable/disable sending welcome SMS on adding a new customer | Medium | Medium
| Configure: Welcome SMS text - Is it the right place? | Medium | Medium
| Pressing 'Back' arrow button to take back to Summary screen | High | Medium
ContactGroupManager?
ShoppingCategoryManager?